## Sheet1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Creating Design | 4 Hours | 14 Hours | 11 Hours | 0 Hours | Design Team
Searching for Tools | 3 Hours | 2 Hour | 1,5 Hours | 0 Hours | Search Team
Inform about Cloud data saving | 5 Hours | 6 Hours | 0 Hours | 6 Hours | Info Team